## KUSHALNAGAR (hidden)
STATIC TO SMART METER TO BE CHANGE REQUEST DETAILS AS ON 28.01.2026
SL NO |  | SIM NO | METER SERIAL NO | PHASE | SECTION | SUBDIVISION | RR NO | STATUS | reason | REMOVED FR | SIM GIVEN DATE
1 |  | 89914509006926872739 | 01002500 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5875 | METER REPLACED |  | 2094 | 28.01.2026
2 |  | 89914509006926872747 | 01002407 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP6238 | METER REPLACED |  | 2933 | 28.01.2026
3 |  | 89914509006926871970 | 01002550 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5934 | METER REPLACED |  | 678 | 28.01.2026
4 |  | 89914509006926871988 | 01002410 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5819 | METER REPLACED |  | 1132 | 28.01.2026
5 |  | 89914509006926871996 | 01002409 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5643 | METER REPLACED |  | 2181 | 28.01.2026
6 |  | 89914509006926872002 | 01002408 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5810 | PENDING IN ONBOARRD |  |  | 28.01.2026
7 |  | 89914509006926872010 | 01002542 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP4901 | ADDED |  |  | 28.01.2026
8 |  | 89914509006926872028 | 01002541 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP6152 | METER REPLACED |  |  | 28.01.2026
9 |  | 89914509006926872036 | 01002497 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP6226 | METER REPLACED |  | 979 | 28.01.2026
10 |  | 89914509006926872044 | 01002498 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP6147 | PENDING |  |  | 28.01.2026
11 |  | 89914509006926871590 | 01002491 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP6156 | PENDING |  | 463 | 30.01.2026 | mla
12 |  | 89914509006926871608 | 01002493 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5291 | PENDING |  |  | 30.01.2026
13 |  | 89914509006926871616 | 01002492 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5940 | PENDING |  | 2313 | 30.01.2026
14 |  | 89914509006926871624 | 01002494 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP6148 | PENDING IN ONBOARRD |  |  | 30.01.2026
15 |  | 89914509006926871632 | 01002600 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP6001 | PENDING |  |  | 30.01.2026
16 |  | 89914509006926871640 | 01002594 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5928 | METER REPLACED |  |  | 30.01.2026
17 | UNMAP | 89914509006926871657 | 01002595 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5341 | PENDING IN ONBOARRD |  |  | 30.01.2026
| MAP | 89914509006926873992 | 01002499 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
18 |  | 89914509006926871665 | 01002593 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5413 | PENDING |  |  | 30.01.2026
19 |  | 89914509006926871673 | 01002591 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5824 | PENDING |  |  | 30.01.2026
20 |  | 89914509006926871681 | 01002592 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5720 | PENDING |  |  | 30.01.2026
21 |  | 89914509006926874032 | W600001239 | THREE | KUSHALNAGAR | KUSHALNAGAR | TP6402 | METER REPLACED |  | 15341 | 31.01.2026
|  | 89914509006926873554 | 01002741 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
|  | 89914509006926873562 | 01002750 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
|  | 89914509006926873570 | 01002713 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
|  | 89914509006926873588 | 01002711 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
|  | 89914509006926873596 | 01002712 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
|  | 89914509006926873893 | 01002504 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
17 | UNMAP | 89914509006926871657 | 01002595 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | TP5341 | PENDING IN ONBOARRD |  |  | 30.01.2026
| MAP | 89914509006926873992 | 01002499 | SINGLE | KUSHALNAGAR | KUSHALNAGAR
17 | UNMAP | 89914509006926871673 | 01002591 | SINGLE | KUSHALNAGAR | KUSHALNAGAR | tp6107 | need to add for meter allocation | in meter display showing meter serial no 01002927 but in meter outer showing serial no 01002591 so cant able to process onboarding plz map new sim and serial no
| MAP | 89914509006926873802 | 01002123 | SINGLE | KUSHALNAGAR | KUSHALNAGAR

## KUDIGE
STATIC TO SMART METER TO BE CHANGE REQUEST DETAILS AS ON 30.01.2026
SL NO |  | SIM NO | METER SERIAL NO | PHASE | SECTION | SUBDIVISION | RR NO | STATUS | remarks | SIM GIVEN DATE
1 |  | 89914509006926871731 | 01002624 | SINGLE | KUDIGE | KUSHALNAGAR | TP6284 | 355 |  | 29.01.2026
2 |  | 89914509006926871715 | 01002622 | SINGLE | KUDIGE | KUSHALNAGAR | TP6272 | 824 |  | 29.01.2026
3 |  | 89914509006926871699 | 01002627 | SINGLE | KUDIGE | KUSHALNAGAR | TP6260 |  |  | 29.01.2026 | 01002621 NO DISPLAY METER NOT WORKING SO PLZ CHANGE TO 01002627 TP6260 SHIRANGALA METER
4 |  | 89914509006926871723 | 01002623 | SINGLE | KUDIGE | KUSHALNAGAR | TP6259 |  |  | 29.01.2026
5 |  | 89914509006926871707 | 01002625 | SINGLE | KUDIGE | KUSHALNAGAR | TP6251 |  |  | 29.01.2026
6 |  | 89914509006926871558 | 01002642 | SINGLE | KUDIGE | KUSHALNAGAR | TP6041 |  |  | 30.01.2026
7 |  | 89914509006926871566 | 01002645 | SINGLE | KUDIGE | KUSHALNAGAR | TP6039 |  |  | 30.01.2026
8 |  | 89914509006926871574 | 01002643 | SINGLE | KUDIGE | KUSHALNAGAR | TP5935 | 2172 |  | 30.01.2026
9 |  | 89914509006926871582 | 01002641 | SINGLE | KUDIGE | KUSHALNAGAR | TP5896 |  |  | 30.01.2026
10 | unmap | 89914509006926874040 | 01002648 | SINGLE | KUDIGE | KUSHALNAGAR | TP5814 | pending in onboarding | this meter gsm not working so meter changed | 30.01.2026
| map | 89914509006926873752 | 01002975
STATIC TO SMART METER REPLACED SO REMOVED FR=2094

## SUNTICOPPA (hidden)
STATIC TO SMART METER TO BE CHANGE REQUEST DETAILS AS ON 05.02.2026
SL NO | SIM NO | METER SERIAL NO | PHASE | SECTION | SUBDIVISION | RR NO | STATUS | REMOVED FR | SIM GIVEN DATE
1 | 89914509006887464138 | 01002735 | SINGLE | SUNTICOPPA | KUSHALNAGAR | STP5664 | done | 1288 | 03.2.2026
2 | 89914509006926872630 | 01002732 | SINGLE | SUNTICOPPA | KUSHALNAGAR | STP5459 | METER COMPLETION done | 535
3 | 89914509006926872622 | 01002736 | SINGLE | SUNTICOPPA | KUSHALNAGAR | STP5913 | METER COMPLETION done | 770 |  | 01002621 NO DISPLAY METER NOT WORKING SO PLZ CHANGE TO 01002627 TP6260 SHIRANGALA METER
| 89914509006926872622 | 01002738
4 | 89914509006926872614 | 01002737 | SINGLE | SUNTICOPPA | KUSHALNAGAR | STP6185 | METER COMPLETION done | 600
5 | 89914509006926872598 | 01002734 | SINGLE | SUNTICOPPA | KUSHALNAGAR | STP5972 | METER COMPLETION done | 506
6 | 89914509006926872606 | 01002731 | SINGLE | SUNTICOPPA | KUSHALNAGAR | STP5360 | METER COMPLETION done | 422
7
8
9
10

## abstract (hidden)
Count of RR No | Column Labels
Row Labels | COMPLETED | PENDING FOR METER ALLOCATION | PENDING FOR METER ONBOARD | Grand Total
123411~KUSHALANAGARA TOWN | 14 | 1 | 4 | 19
123412~KUDIGE | 7 |  | 3 | 10
123421~SUNTIKOPPA | 7 |  | 1 | 8
Grand Total | 28 | 1 | 8 | 37

## all (hidden)
Accountid | RR No | Last Reading Date | Remove Kwh | Remove Kvah | Mc Units | New Meter Sr.No | In Read KWH | In Read KVAH | Status | section | Download
C234102056 | TP5643 | 2026-01-02 | 2181 | 0 | 0 | 1002409 | 0 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234102519 | TP5819 | 2026-01-02 | 1132 | 0 | 33 | 1002410 | 1 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234102759 | TP5875 | 2026-01-02 | 2094 | 0 | 157 | 1002500 | 7 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234102995 | TP5928 | 2026-03-02 | 2534 | 0 | 1 | 1002594 | 1 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234103051 | TP5933 | 2026-01-02 | 16565 | 0 | 183 | W600001232 | 3 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234103066 | TP5934 | 2026-01-02 | 678 | 0 | 0 | 1002550 | 0 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234103079 | TP5940 | 2026-03-02 | 2313 | 0 | 128 | 1002492 | 0 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234103308 | TP6001 | 2026-04-02 | 1458 | 0 | 46 | 1002600 | 1 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234103832 | TP6156 | 2026-05-02 | 460 | 0 | 21 | 1002491 | 0 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234103869 | TP6152 | 2026-04-02 | 1182 | 0 | 67 | 1002541 | 0 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234104037 | TP6182 | 2026-07-02 | 1074 | 6 | 232 | W600001235 | 2 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234104210 | TP6226 | 2026-01-02 | 979 | 0 | 14 | 1002497 | 0 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234104265 | TP6238 | 2026-01-02 | 2933 | 0 | 0 | 1002407 | 0 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234105219 | TP6402 | 2026-01-02 | 15341 | 0 | 0 | W600001239 | 1 |  | COMPLETED | 123411~KUSHALANAGARA TOWN
C234102843 | TP5896 | 2026-06-02 | 1810 | 0 | 1 | 1002641 | 2 |  | COMPLETED | 123412~KUDIGE
C234103065 | TP5935 | 2026-06-02 | 2172 | 0 | 0 | 1002643 | 0 |  | COMPLETED | 123412~KUDIGE
C234103426 | TP6039 | 2026-06-02 | 3284 | 0 | 1 | 1002645 | 3 |  | COMPLETED | 123412~KUDIGE
C234103429 | TP6041 | 2026-07-02 | 831 | 0 | 8 | 1002642 | 3 |  | COMPLETED | 123412~KUDIGE
C234104336 | TP6259 | 2026-07-02 | 839 | 0 | 0 | 1002623 | 3 |  | COMPLETED | 123412~KUDIGE
C234104337 | TP6260 | 2026-07-02 | 1962 | 0 | 8 | 1002627 | 0 |  | COMPLETED | 123412~KUDIGE
C234104824 | TP6284 | 2026-07-02 | 355 | 0 | 15 | 1002624 | 4 |  | COMPLETED | 123412~KUDIGE
C234200340 | STP5360 | 2026-04-02 | 422 | 0 | 4 | 1002731 | 1 |  | COMPLETED | 123421~SUNTIKOPPA
C234200414 | STP5459 | 2026-04-02 | 535 | 0 | 10 | 1002732 | 3 |  | COMPLETED | 123421~SUNTIKOPPA
C234200729 | STP5664 | 2026-02-02 | 1288 | 0 | 177 | 1002735 | 34 |  | COMPLETED | 123421~SUNTIKOPPA
C234200732 | STP5678 | 2026-01-02 | 6739 | 0 | 14 | W600001930 | 2 |  | COMPLETED | 123421~SUNTIKOPPA
C234201161 | STP5972 | 2026-04-02 | 507 | 0 | 0 | 1002734 | 1 |  | COMPLETED | 123421~SUNTIKOPPA
C234201438 | STP6169 | 2026-01-02 | 10032 | 0 | 507 | W600001928 | 2 |  | COMPLETED | 123421~SUNTIKOPPA
C234201443 | STP6185 | 2026-04-02 | 600 | 0 | 8 | 1002737 | 2 |  | COMPLETED | 123421~SUNTIKOPPA
C234103828 | TP6147 | 2026-04-02 | 1916 | 0 | 41 |  |  |  | PENDING FOR METER ALLOCATION | 123411~KUSHALANAGARA TOWN
C123410022 | TP4901 | 14-01-2026 | 1385 | 0 | 1075 | 1002542 |  |  | PENDING FOR METER ONBOARD | 123411~KUSHALANAGARA TOWN
C234100953 | TP5341 | 2026-03-02 | 1941 | 0 | 110 | 1002499 |  |  | PENDING FOR METER ONBOARD | 123411~KUSHALANAGARA TOWN
C234102505 | TP5810 | 2026-04-02 | 2191 | 0 | 42 | 1002408 |  |  | PENDING FOR METER ONBOARD | 123411~KUSHALANAGARA TOWN
C234103830 | TP6148 | 2026-04-02 | 607 | 0 | 3 | 1002494 |  |  | PENDING FOR METER ONBOARD | 123411~KUSHALANAGARA TOWN
C234102526 | TP5814 | 2026-04-02 | 2620 | 0 | 75 | 1002648 |  |  | PENDING FOR METER ONBOARD | 123412~KUDIGE
C234104340 | TP6251 | 2026-07-02 | 478 | 0 | 25 | 1002625 |  |  | PENDING FOR METER ONBOARD | 123412~KUDIGE
C234104475 | TP6272 | 2026-07-02 | 824 | 0 | 11 | 1002622 |  |  | PENDING FOR METER ONBOARD | 123412~KUDIGE
C234201021 | STP5913 | 2026-09-01 | 770 | 0 | 1 | 1002736 |  |  | PENDING FOR METER ONBOARD | 123421~SUNTIKOPPA